## Milestone,Target Date (2026),Ac
Milestone | Target Date (2026) | Acceptance Evidence | Dependencies | Payment Trigger (HKD) | Notes
Kickoff Meeting | Jan 20 | Kickoff minutes signed | Client provides primary contacts | 0 | Includes RACI confirmation
Environment Access Granted | Jan 25 | Email confirmation from ClientCo | Client IT grants M365 admin; VPN test | 0 | Access delays may shift onboarding
Onboarding Complete | Feb 05 | Handover checklist signed | RMM deployed to 85 devices | 0 | All devices must report healthy
Month 1 Service Delivery | Feb 29 | Monthly report + invoice | Onboarding complete | 68000 | First billable month
Month 2 Service Delivery | Mar 31 | Monthly report + invoice | ServiceMonth1 completed | 68000 | Subject to SLA adherence
Stakeholder Review | Apr 05 | Review notes logged | Month1 & 2 reports | 0 | Quarterly cadence thereafter